## How to use
GroundsTruth DMS — Delivery Tracker
Campa DMS · step-by-step build plan for Aman & Hardik · starts after inception + during requirement gathering
Tabs in this workbook:
0 · Pre-Build | Steps that run right after inception, while requirement gathering is underway.
1 · MVP (Phase 1) | Very low-level steps per module to deliver the MVP — go-live in 4 weeks.
2 · Phase 2 | Low-level steps for the core production phase — go-live in 6 weeks.
3 · Milestones | Payment + acceptance gates tied to the steps.
How to work it:
Status | Use the dropdown: Not started / In progress / Blocked / Done.
Owner | Default 'Both'. Client-facing steps note 'Aman on paper'. Decide actual split mutually.
Depends on | The step ID(s) that must be Done before this starts. Don't start a step with open dependencies.
Est (hrs) | Rough effort to plan around Hardik's part-time availability — not a commitment.
Sequencing principle: | Build the anti-leakage core (inventory + invoice + reconciliation) earliest; it's why the system exists.
Clock-start rule: | MVP build steps assume all BLOCKER inputs are in hand (see Intake Checklist).

## 0 · Pre-Build
0 · Pre-Build
ID | Module | Step (low-level) | Deliverable / output | Depends on | Owner | Est (hrs) | Status | Notes
A · Foundations (legal + accounts) — in parallel with requirement gathering
P01 | Setup | Sign Founders' Agreement & IP Licence | Signed docs 1 & 2 |  | Both | 2 | Not started | Internal
P02 | Setup | Create shared GroundsTruth mailbox + password manager | Gmail + vault |  | Both | 1 | Done
P03 | Setup | Open collection account / confirm payment routing | Account ready | P01 | Both | 2 | Not started | Aman personal a/c per agreement; CA check on HUF
P04 | Setup | Send NDA, then MSA+SOW to client; collect advance | Signed MSA + ₹2L |  | Both (Aman on paper) | 3 | Done
P05 | Setup | Provision tool accounts: LLM, hosting, DB, Maps, Resend, messaging | Accounts + billing | P02 | Both | 3 | Done | Bundle billed pass-through (~₹50k)
B · Requirement gathering & sign-off (drives everything below)
P06 | Requirements | Run requirement questionnaire session with client | Filled Doc 5 | P04 | Both (Aman on paper) | 4 | Not started
P07 | Requirements | Collect all BLOCKER inputs (SKU master, retailer list, invoice/challan samples, GSTIN, staff, brand) | Doc 6 all ✓ | P06 | Both (Aman on paper) | 4 | Not started | Clock starts when complete
P08 | Requirements | Confirm sales model (pre-sell / deliver / hybrid) in writing | Written confirmation | P06 | Both (Aman on paper) | 1 | Not started
P09 | Requirements | Capture UI/brand preferences | Filled Doc 7 | P06 | Both (Aman on paper) | 2 | In progress
P10 | Requirements | Get CA sign-off on invoice/challan format | CA email | P07 | Both (Aman on paper) | 2 | Blocked | Third-party gated
P11 | Requirements | Agree per-feature acceptance criteria → MSA Schedule C | Acceptance list | P06 | Both | 2 | Blocked
C · Technical foundation (can start as inputs firm up)
P12 | Design | Finalise architecture diagram + confirm tech stack | Architecture sign-off | P08 | Both | 4 | Not started | Use HLD doc as base
P13 | Design | Finalise ER schema + migration plan | Schema v1 | P12 | Both | 5 | Not started
P14 | Design | Define API contract (endpoints, payloads, auth) | API spec | P12 | Both | 4 | Not started
P15 | DevOps | Create repo, branch strategy, CI pipeline | Repo + CI | P05 | Both | 3 | In progress
P16 | DevOps | Provision dev + staging env, DB, object store, secrets | Envs live | P15 | Both | 4 | In progress
P17 | DevOps | Scaffold app from licensed base components | Skeleton runs | P16 | Both | 3 | Done
P18 | Design | Design system / UI kit from brand workbook (colours, components) | UI kit | P09 | Both | 5 | In progress

## 1 · MVP (Phase 1)
1 · MVP (Phase 1)
ID | Module | Step (low-level) | Deliverable / output | Depends on | Owner | Est (hrs) | Status | Notes
M0 · Cross-cutting scaffolding (build once, used by all modules)
M01 | Platform | DB migrations for core tables (users, roles, skus, inventory, orders, order_lines, invoices, van_loads, collections, audit_log) | Schema in dev | P13,P17 | Hardik | 6 | Not started
M02 | Platform | Audit logging hook (every mutation writes audit_log) | AuditService | M01 | Hardik | 4 | Not started | Liability hotspot — do early
M03 | Platform | Config layer (tax slabs, invoice series, thresholds, discount ceiling, recon tolerance) | Config tables/seed | M01 | Hardik | 4 | Not started
M04 | Platform | Error/empty/no-network UI states + idempotency on key POSTs | Shared UX states | P17 | Aman | 4 | In progress | No offline — surface clearly
M1 · Auth & RBAC
M05 | Auth | OTP request + verify (SMS) flow | OTP login | M01,P05 | Both | 6 | Not started
M06 | Auth | JWT issue with role claim + refresh | Token auth | M05 | Both | 4 | Not started
M07 | Auth | RBAC middleware + permission map per role | Authorisation | M06 | Both | 5 | Not started
M08 | Auth | User CRUD + role assignment (owner screen) | User mgmt UI | M07 | Both | 5 | Not started
M09 | Auth | Acceptance: each role sees only permitted screens | Test pass | M08 | Both | 2 | Not started | Acceptance criterion
M2 · Catalog & Inventory (anti-leakage foundation)
M10 | Inventory | SKU master CRUD + import (sizes, MRP, HSN, tax slab, units/case) | Catalog | M03 | Aman | 6 | In progress | SKU master live on Supabase (46 seeded, migration 0001), read at /catalog. CRUD/import + MRP/HSN/tax/cess pending.
M11 | Inventory | Stock model with batch + expiry; qty>=0 constraint | Inventory tables | M10 | Hardik | 5 | Not started
M12 | Inventory | Inward stock (receive) + stock view by SKU/batch | Receive + view | M11 | Hardik | 5 | Not started
M13 | Inventory | FIFO deduction service (oldest batch first) — transactional | deductStock() | M11,M02 | Hardik | 6 | Not started | Core; called by invoicing
M14 | Inventory | Low-stock alert rule + flag on dashboard | Low-stock alerts | M12,M03 | Hardik | 4 | Not started
M15 | Inventory | Acceptance: receive stock, deduct, balance correct & audited | Test pass | M13 | Hardik | 2 | Not started
M3 · Retailer onboarding
M16 | Retailer | Retailer CRUD + import (name, shop, address, phone, GSTIN, beat) | Retailers | M01 | Both | 5 | Not started
M17 | Retailer | Field onboarding form (photo/geo optional) + approval rule | Onboarding UI | M16,M07 | Both | 5 | Not started
M4 · Sales & Invoicing (the money path)
M18 | Sales | Price-list rule (price per SKU per retailer/region) | priceLine() | M10,M16 | Hardik | 5 | Not started
M19 | Sales | Order punch UI + order/order_lines model | Create order | M18,M07 | Hardik | 7 | Not started
M20 | Sales | Invoice number service (server-side, configured series) | Numbering | M03 | Hardik | 3 | Not started
M21 | Sales | Invoice generation (tax compute to CA spec) + PDF render | Invoice + PDF | M20,P10 | Hardik | 8 | Not started | Build to signed-off format
M22 | Sales | confirmAndInvoice(): invoice + stock deduct in ONE transaction | Atomic invoice | M21,M13 | Hardik | 6 | Not started | Critical atomicity
M23 | Sales | Acceptance: punch order → invoice → stock auto-deducts | Test pass | M22 | Hardik | 2 | Not started | Headline acceptance criterion
M5 · Van loading, challan & reconciliation (anti-leakage core)
M24 | Van | Van load-out (qty_out per SKU) + load sheet | loadVan() | M11 | Hardik | 5 | Not started
M25 | Van | Delivery challan generation to client format | Challan PDF | M24,P10 | Hardik | 5 | Not started
M26 | Van | Return-stock capture (qty_returned) | recordReturns() | M24 | Hardik | 4 | Not started
M27 | Van | Reconciliation: out − sold − returned; stock↔sales↔cash variance flag | reconcile() | M26,M22 | Hardik | 7 | Not started | The reason the system exists
M28 | Van | Acceptance: variance beyond tolerance flags to owner + audit | Test pass | M27 | Hardik | 2 | Not started
M6 · Collection + Owner Dashboard
M29 | Collection | Record cash/UPI against invoice (ref captured, not processed) | recordCollection() | M22 | Hardik | 4 | Not started
M30 | Dashboard | Owner dashboard: daily sales, collections, low-stock, variance flags | Dashboard | M29,M27,M14 | Aman | 7 | In progress | Top-5 numbers from client
M31 | Dashboard | Daily sales view (by van/rep/SKU as scoped) | Daily sales | M30 | Aman | 4 | In progress | Daily sales view from seed; wire to live aggregates.
M7 · Hardening, pilot & go-live (Phase 1)
M32 | QA | Automated tests on critical paths (invoice atomicity, recon math, RBAC, discount ceiling) | Test suite | M23,M28 | Both | 6 | Not started
M33 | QA | Full QA pass against all Phase-1 acceptance criteria | QA report | M32 | Both | 5 | Not started
M34 | DevOps | Backups + restore runbook; monitoring/alerting | Ops ready | M16 | Both | 4 | Not started
M35 | Pilot | Load real master data; pilot with 2–3 users on staging | Pilot sign-off | M33,P07 | Both (Aman on paper) | 5 | Not started
M36 | Release | Deploy to prod; client demo + Phase-1 acceptance | Go-live (4 wks) | M35 | Both (Aman on paper) | 3 | Not started

## 2 · Phase 2
2 · Phase 2
ID | Module | Step (low-level) | Deliverable / output | Depends on | Owner | Est (hrs) | Status | Notes
X0 · Phase 2 start (after Phase-1 milestone paid)
X01 | Platform | Migrations for Phase-2 tables (ledger_entries, attendance, beats, pod, discounts) | Schema v2 | M36 | Both | 5 | Not started
X1 · Beat planning + GPS check-in
X02 | Field | Beat model + assign reps to beats/routes | Beats | X01 | Both | 5 | Not started
X03 | Field | GPS check-in at retailer visit (Maps API) | Geo check-in | X02,P05 | Both | 6 | Not started
X2 · Attendance
X04 | Field | Attendance (check-in/out, optional geo-fence) + view | Attendance | X01 | Both | 6 | Not started
X3 · Retailer ledger + credit
X05 | Ledger | Append-only ledger entries + running balance | LedgerService | X01,M29 | Both | 6 | Not started
X06 | Ledger | Credit limit + outstanding check on order | Credit control | X05,M19 | Both | 5 | Not started
X07 | Ledger | Outstanding/overdue alerts | Alerts | X06 | Both | 4 | Not started
X4 · Geo-tagged proof-of-delivery
X08 | Field | PoD capture (photo + geo-tag + signature) | PoD | X03 | Both | 6 | Not started
X5 · Discounting
X09 | Sales | Discount on orders, bounded by approval ceiling | applyDiscount() | M19,M03 | Both | 5 | Not started | Cannot exceed ceiling
X6 · Alerts router (WhatsApp / push)
X10 | Notify | Notification router; low-stock & payment alerts via WhatsApp/push | NotificationService | X07,M14,P05 | Both | 6 | Not started
X7 · Reporting + dashboard
X11 | Reports | Daily sales report (DSR) generation + delivery | DSR | M31 | Both | 5 | Not started
X12 | Dashboard | Richer owner dashboard (Phase-2 metrics) | Dashboard v2 | X11,X05 | Both | 5 | Not started
X8 · Hardening & go-live (Phase 2)
X13 | QA | QA pass on Phase-2 acceptance criteria | QA report | X02,X04,X06,X08,X09,X10,X12 | Both | 6 | Not started
X14 | Release | Deploy; client demo + Phase-2 acceptance | Go-live (6 wks) | X13 | Both (Aman on paper) | 3 | Not started
X15 | Support | 15-day free support window begins | Support live | X14 | Both |  | Not started
X16 | Support | Offer AMC + pitch roadmap add-ons (offline, schemes, analytics) | Recurring + upsell | X14 | Both (Aman on paper) | 2 | Not started

## Milestones
Payment & Acceptance Milestones
Milestone | Gate (steps complete) | Amount | Status
Advance (before dev) | MSA signed (P04) | ₹2,00,000 | Not started
Software/infra bundle | Tools provisioned (P05) | ~₹50,000 (est) | Not started
Phase 1 (MVP) delivery | Go-live + acceptance (M36) | ₹2,50,000 | Not started
Phase 2 delivery | Go-live + acceptance (X14) | ₹50,000 | Not started
AMC (optional) | After 15-day free support (X15) | ₹10,000/mo or ₹1L/yr | Not started