# Build Kickoff & Next Steps

GroundsTruth DMS · starting from the Jaypee June-2026 workbook · internal

Decision: start the data-true core now, ask six questions in parallel. The Jaypee workbook is a real operational export — it confirms the SKU list, the sales schema, the route/van model and how stock-vs-sales is reconciled. That is enough to begin the inventory–sales–reconciliation engine immediately. It does NOT contain invoicing/tax, retailer, or batch/expiry data, so those parts wait on short answers. Nothing about the build needs to be fully blocked.

# 1. What we now have (seed assets)

- seed_skus.csv / seed_skus.sql — 52 SKUs (CSD Cola/Orange/Lemon across 200ml–2L, Campa 2.25L, Water, Gold Boost Energy, Energy Berry Kick, Rasiki, Soda) with rate-per-case where known. MRP / HSN / tax-slab left as explicit TODO columns.

- seed_sales_sample.csv — real sales lines in the source schema: timestamp, date, route_id, article_name, qty_sold, rate, line_total, data_source (WHATSAPP_API), order_id.

- Confirmed operating model — WhatsApp-API-driven sales, organised by routes/vans (Route-1…Route-7, six vans + warehouse), daily van load-out and a manual stock↔sales reconciliation we are automating.

# 2. Start NOW (workbook de-risks these)

These map to tracker steps P12–P17 and the M0–M2 / M5 blocks. We are not guessing on any of them.

| Step | What | Backed by |
| --- | --- | --- |
| Project setup | Vercel + Next.js app, Supabase project, repo + CI, dev/staging envs | Stack decided |
| Schema + migrations | skus, inventory, van_loads, van_load_lines, sales/order_lines, audit_log + RLS | Sales schema confirmed |
| SKU master seed | Load the 52 SKUs from seed_skus.sql | seed_skus.csv/sql |
| Inventory + inward stock | Stock on hand, daily inward, low-stock flag | MASTER_INVENTORY sheet |
| Van load model | Per-van per-article load-out + returns | VAN_PERFORMANCE sheet |
| Sales ingestion | Order/sales lines in the confirmed grain | API_RAW_DUMP schema |
| Reconciliation core | out − sold − returned → variance flag | SALES_VS_STOCK sheet |
| Auth + RLS | OTP login, roles, row-level policies | Design done |

# 3. HOLD until the six answers (don’t build twice)

| On hold | Blocked by question |
| --- | --- |
| Invoice + challan generation, tax compute | Q1 — GST/HSN/cess per SKU, invoice format + numbering, CA sign-off (or confirmation they don’t invoice). |
| Retailer onboarding + retailer ledger/credit | Q2 — do they track individual retailers, or route-only? (Workbook has NO retailer entity.) |
| Batch/expiry + FIFO, MRP display | Q3 — do they track batch/expiry, or only qty on hand? MRP per SKU? |
| Order-capture design | Q4/Q5 — confirm van pre-sell; are we replacing the WhatsApp flow or ingesting from it? |
| Manual discounting | Q6 — discount ceiling + whether schemes exist. |

# 4. The six bare-minimum questions (one short call)

- Invoicing & tax — do they issue invoices? If yes: GST/HSN/cess per SKU, format, numbering, CA sign-off. (Biggest unknown.)

- Retailers — individual shops as entities, or route-only? Decides whether onboarding/ledger tables get built or descoped.

- Inventory — batch/expiry tracked (FIFO) or just on-hand? MRP per SKU?

- Sales model — confirm WhatsApp-driven van pre-sell.

- WhatsApp-API source — are we replacing it or feeding off it? Affects the whole order-capture design.

- Discount ceiling + any buy-X-get-Y schemes (engine is later, but manual discounting needs the boundary).

One-line confirmation also needed: the workbook is labelled “Jaypee Advertisers” — confirm this is the actual contracted client’s real data and SKU set, not a sample from elsewhere, before we seed from it.

# 5. Sequence for the next two weeks

| When | Do |
| --- | --- |
| Day 1–2 | Vercel + Supabase project; repo, CI, dev/staging; load seed_skus.sql; stand up auth (OTP) + roles + RLS skeleton. |
| Day 2–3 | Send the six questions to client (Aman fronts). In parallel: build inventory + inward stock + low-stock. |
| Day 3–5 | Van load model + returns; sales ingestion in the confirmed grain; wire audit logging on every mutation. |
| Day 5–7 | Reconciliation core (variance flag) — the anti-leakage spine — modelled on SALES_VS_STOCK. Owner dashboard skeleton. |
| On answers | Unblock invoicing/tax, retailer, batch/expiry. Build invoice + challan to the signed-off format; decide retailer scope. |
| Then | Collection + dashboard → QA against acceptance criteria → pilot with 2–3 users → Phase-1 go-live. |

# 6. Guardrails while starting early

- Keep the invoice/tax and retailer modules behind clean seams so adding them later doesn’t disturb the core.

- Treat the seed data as a starting point, not gospel — re-import the client’s authoritative master once confirmed.

- Reconciliation + audit logging from day one (the liability hotspot); never invoice without atomic stock deduct.

- Don’t hardcode tax/numbering/discount/tolerance — config from the start, since these arrive from the client late.

Net: you can start roughly half the MVP today on solid ground, and the half you can’t is unblocked by a single 30-minute call — faster than waiting for full requirement-gathering, and without building anything twice.